## FRONTPAGE
Railway Project, Pre-engineering phase 2
VERSION HISTORY
VERSION | DATE | AUTHOR | CHANGE
0.1 | 21.10.2016 | Toni Hytönen | Workshop 1 results
0.2 | 3.11.2016 | Toni Hytönen | Workshop 2 results
0.3 | 7.11.2016 | Toni Hytönen | Workshop 3 results
0.4 | 9.11.2016 | Toni Hytönen | Workshop 4 results
0.5 | 15.11.2016 | Toni Hytönen | Finalizing
0.6 | 26.11.2016 | Toni Hytönen | Finalizing
0.7 | 28.11.2016 | Toni Hytönen | Meetings in Uruguay and reordering and combining similar hazards
1.0 | 1.12.2016 | Toni Hytönen | Finalizing
1.1 | 9.12.2016 | Toni Hytönen | Finalizing
1.2 | 14.12.2016 | Toni Hytönen | New hazards and final version for phase 1
1.3 | 14.2.2017 | Toni Hytönen | New risks from comments added
1.4 | 6.6.2017 | Toni Hytönen ja Outi Erälaukko | Road and street, geotechnics risk workshop
1.5 | 14.6.2017 | Toni Hytönen ja Outi Erälaukko | Bridge risk workshop and other cleaning up
1.6 | 15.6.2017 | Toni Hytönen | Trench risk workshop
1.7 | 27.6.2017 | Toni Hytönen | Categorizing hazards
1.8 | 28.6.2017 | Toni Hytönen | Small changes to hazards
1.9 | 29.6.2017 | Toni Hytönen | Small changes to hazards
2.0 | 30.6.2017 | Toni Hytönen | Small changes to hazards
2.1 | 19.7.2017 | Toni Hytönen | Updated risk matrix according to Jorge Setelich comments, workshops and overview
2.2 | 15.8.2017 | Toni Hytönen | Bridge risk workshop
2.3 | 16.8.2017 | Toni Hytönen | Construction and maintenance
2.4 | 22.8.2017 | Toni Hytönen | Project risks
2.5 | 23.8.2017 | Toni Hytönen | Road and street risk workshop
2.6 | 24.8.2017 | Toni Hytönen | Geotechnics and rail workshop and finalizing hazard record
2.7 | 28.8.2017 | Toni Hytönen | Finalizing
2.8 | 1.9.2017 | Toni Hytönen | Changes from comments (A.M. 30.8.2017)
3.0 | 23.10.2017 | Toni Hytönen | Final version for phase 2 (only terminological changes)

## HAZARD RECORD
HAZARD RECORD
Railway Project, Pre-engineering phase 2
DATE | 2017-10-23 | [20 empty] | SECRET
VERSION | 3.0
LIFE CYCLE PHASE
HAZARD ID | HAZARD IDENTIFIED AT | HAZARD | HAZARDOUS SITUATION AND CONSEQUENCES | DESIGN | CONSTRUCTION | COMMISSIONING | OPERATION | HAZARD TYPE | DISCIPLINE | EXISTING MEASURES AND ASSUMPTIONS | FREQUENCY | SEVERITY | RISK LEVEL | MEASURES | FREQ. RES. | SEV. RES. | RESIDUAL RISK LEVEL | PERSON/ORGANIZATION IN CHARGE | IMPLEMENTED SAFETY MEASURES /REQUIREMENTS | STATE OF MEASURES | STATE OF HAZARD | UPDATE
1 | Risk workshop 1 21.10.2016 | Removing existing level crossings | Congestation of the other level crossings and detours. Impact on local communities and traffic. Approval will be reduced, effects on timetable and costs. |  | X |  | X | ENVIRONMENT AND SOCIAL | ROAD AND STREET | Simulations has been made in southern rural areas Many level crossings are preserved. | 5 | 1 | Minor | List of railway level crossings' properties and measures. Environment Impact Assessment and permitting Public meetings, education and information of the railway Road traffic simulations | 4 | 1 | Negligible | LKSur GoU CSI | List of railway level crossings' properties and measures and type designs has been done. (VR Track Oy) EIA in progress Simulations of traffic has been done | PARTIALLY IMPLEMENTED | CONTROLLED | 2017-09-01
2 | Risk workshop 1 21.10.2016 | Conflict between area planning and railway area | New railway tracks limits the use of land near railway area in the future Impact on regional planning. Approval will be reduced, effects on timetable and costs | X |  |  |  | ENVIRONMENT AND SOCIAL | RAIL | Reserved railway area is quite large and the need for new land is minimal. | 4 | 2 | Minor | Environment Impact Assessment and permitting | 2 | 2 | Negligible | LKSur | Reginal planning zones are known. | PARTIALLY IMPLEMENTED | CONTROLLED | 2017-08-24
3 | Risk workshop 1 21.10.2016 | Buildings and structures in railway area. | Removing buildings and structures causes opposition and administrative process is slow Approval will be reduced, effects on timetable and costs | X | X |  |  | ENVIRONMENT AND SOCIAL | RAIL |  | 5 | 3 | Significant | List of identifyed buildings in railway area. Environment Impact Assessment and permitting Public meetings, education and information of the railway | 2 | 3 | Minor | LKSur GoU | Lazer scanning by air has been done. | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
4 | Risk workshop 1 21.10.2016 | Train traffic 24 hours a day, heavier axle load and higher speeds | Noise and vibration from rolling stock and level crossing's alarm systems during night time. Health and environment issues during operation. |  |  |  | X | ENVIRONMENT AND SOCIAL | ENVIRONMENT |  | 5 | 2 | Moderate | Environment Impact Assessment and permitting | 5 | 2 | Moderate | LKSur | EIA in progress | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
5 | Risk workshop 1 21.10.2016 | Building near protected buildings, monuments and other structures | Protected buildings, monuments and other structures are damaged during construction or has to be moved. Approval will be reduced, effects on timetable and costs |  | X |  |  | ENVIRONMENT AND SOCIAL | ENVIRONMENT | Map of landscape and culture objects in Uruguay is available online Reserved railway area is quite large and the need for new land is minimal. | 4 | 2 | Minor | Environment Impact Assessment and permitting | 4 | 2 | Minor | LKSur | EIA in progress | PARTIALLY IMPLEMENTED | CONTROLLED | 2017-08-24
6 | Risk workshop 1 21.10.2016 | Building near nature reserve or reserved species | Impact on nature reserve or reserved species during construction Approval will be reduced, effects on timetable and costs |  | X |  |  | ENVIRONMENT AND SOCIAL | ENVIRONMENT | Reserved railway area is quite large, need for new land is minimal | 4 | 2 | Minor | Environment Impact Assessment and permitting | 4 | 2 | Minor | LKSur | EIA in progress | PARTIALLY IMPLEMENTED | CONTROLLED | 2017-08-24
7 | Risk workshop 1 21.10.2016 | Building near surface water and groudwater area | Impact on ground water level, contamination or guiding the water flow Approval will be reduced, effects on timetable and costs, maintenance problems |  | X |  | X | ENVIRONMENT AND SOCIAL | ENVIRONMENT |  | 4 | 4 | Significant | Environment Impact Assessment and permitting | 4 | 4 | Significant | LKSur | EIA in progress | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
8 | Risk workshop 2 3.11.2016 | Heavy rain and insufficent drainage | Flood on the tracks or on the roads/streets (underpass especially). Effects on track structures and devices or underpasses. Traffic delays and maintenance problems |  | X |  | X | RAILWAY SYSTEM | RAIL |  | 5 | 2 | Moderate | Study of the current situation, list of the critical flood areas and measures. | 5 | 1 | Minor | Railway Contractor | Some flood areas are know, not fully implemented (VR Track Oy). | PARTIALLY IMPLEMENTED | OPEN | 2017-09-01
9 | Risk workshop 1 21.10.2016 | New land mass has to be transported from a far or the existing land mass has to be stored/processed far away | Impact on environment, costs and safety |  | X |  |  | TIMETABLE AND COST | ENVIRONMENT |  | 5 | 3 | Significant | Mass balance analysis (input and output). Survey of locations, transportation and amount. Environment Impact Assessment and permitting. | 5 | 3 | Significant | Railway Contractor LKSur |  | OPEN | OPEN | 2017-08-24
10 | Risk workshop 1 21.10.2016 | Existing contaminated soil | Handling contaminated soil in the construction or maintenance. Processing contaminated soil is expensive. Work safety and health issues and environment impact. |  | X |  | X | ENVIRONMENT AND SOCIAL | ENVIRONMENT |  | 5 | 2 | Moderate | Environment Impact Assessment and permitting | 5 | 2 | Moderate | LKSur | EIA in progress | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
11 | Risk workshop 1 21.10.2016 | Environment assessment and measures are not monitored during the process | Requirements and promises are not fulfilled. Approval will be reduced, effects on timetable and costs | X | X | X | X | ENVIRONMENT AND SOCIAL | ENVIRONMENT |  | 2 | 4 | Moderate | Environment Impact Assessment and permitting | 2 | 4 | Moderate | LKSur | EIA in progress | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
12 | Risk workshop 1 21.10.2016 | Railway accident (collision or derailment) | Leakage on the rolling stock, track soil is contaminated. Impact on maintenance cost and work safety and health issues |  |  |  | X | ENVIRONMENT AND SOCIAL | ENVIRONMENT |  | 5 | 3 | Significant | Defining maintenance standards Operation rules for dangerous goods accidents | 4 | 2 | Minor | GoU | First draft of the maintenance standards has been done (VR Track Oy) | IMPLEMENTED | CONTROLLED | 2017-08-24
13 | Risk workshop 2 3.11.2016 | Walking on the tracks Stations and platforms in rural areas are used for accommodation, parking and other activities Railway area is not physically or visually separated from surrounding area | Unauthorized personel on the rail tracks. Accidents to persons caused by rolling stock in motion. |  |  |  | X | RAILWAY SYSTEM | RAIL | It is common to be on tracks because traffic is predictable, slow and quite rare. Railway tracks are not considered to be dangerous. Increase in freight train traffic and higher speeds increases the propability for accident. | 5 | 4 | Critical | List of railway level crossings' properties and measures. Fencing, tracks on a higher/lower level, dikes and other structural means Defining regulation and rules for moving in railway area Public meetings, education and information of the railway | 4 | 4 | Significant | GoU | List of railway level crossings' properties and measures and type designs has been done. (VR Track Oy) Fencing almost all the along track | PARTIALLY IMPLEMENTED | OPEN | 2017-09-01
16 | Risk workshop 2 3.11.2017 | Behaviour in level crossings, safety culture | Stopping at the level crossing on the tracks / going over the tracks at last moments possible / ignoring stop signs, speed limits Accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | ROAD AND STREET | Speed limit 60 km/h for train traffic in city area. Almost 240 level crossings | 5 | 4 | Critical | List of railway level crossings' properties and measures. Defining regulation and rules for moving in railway area Public meetings, education and information of the railway Alarm time of the signaling device has to be optimized | 4 | 4 | Significant | GoU | List of railway level crossings' properties and measures and type designs has been done. (VR Track Oy) | PARTIALLY IMPLEMENTED | OPEN | 2017-09-01
18 | Risk workshop 2 3.11.2016 | Railway bridge is used by pedestrians | Unauthorized persons on the railway. Accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | BRIDGE |  | 2 | 4 | Moderate | Passage for pedestrians on the bridge Defining regulation and rules for moving in railway area Public meetings, education and information of the railway | 2 | 4 | Moderate | GoU | Passages for pedestrians planned | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
19 | Risk workshop 2 3.11.2016 | Vandalism | Breaking, demolishing or stealing construction equipment or material or track equipment Impact on cost and timetable |  | X |  | X | RAILWAY SYSTEM | SIGNALLING |  | 5 | 2 | Moderate | Work area plan Covering signaling cables (heavy cover, cover openable only with special tools etc) Camera surveillance as needed | 5 | 2 | Moderate | Railway Contractor GoU |  | OPEN | OPEN | 2017-08-24
21 | Risk workshop 2 3.11.2016 | Level crossing area is not defined and clearly sepatared | Accident to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | ROAD AND STREET | Speed limit 60 km/h for train traffic in city area. | 5 | 4 | Critical | List of railway level crossings' properties and measures. | 2 | 4 | Moderate |  | List of railway level crossings' properties and measures and type designs has been done. (VR Track Oy) | IMPLEMENTED | CONTROLLED | 2017-09-01
22 | Risk workshop 2 3.11.2016 | Line of sight is poor to none and/or the angle of the railway and road is significantly less or more then 90 degrees | Pedestrian or vehicle can't detect incoming train Accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | ROAD AND STREET | Speed limit 60 km/h for train traffic in city area. Almost 240 level crossings | 5 | 4 | Critical | List of railway level crossings' properties and measures. Measures for fault situations Maintenance plan | 4 | 4 | Significant | GoU | List of railway level crossings' properties and measures and type designs has been done. (VR Track Oy) | PARTIALLY IMPLEMENTED | OPEN | 2017-09-01
24 | Risk workshop 2 3.11.2016 | Operation rules and training in normal situation and in contingency situation are insufficient for the operation of the new train control system | Collions accidents, derailments and accidents to persons caused by rolling stock in motion and level-crossing accidents |  |  |  | X | RAILWAY SYSTEM | SIGNALLING |  | 4 | 5 | Critical | Defining roles, responsibilities and competence for all parties in railway system Safety management system for Infrastructure Manager and Railway Operator | 1 | 5 | Moderate | GoU, Railway Operator and Infrastructure Manager GoU, Railway Operator and Infrastructure Manager |  | OPEN | OPEN | 2017-08-24
25 | Risk workshop 2 3.11.2016 | Maintenance of the track is insufficient | Damage to infrastructure (rail or point) --> delay in train traffic, derailment |  |  |  | X | RAILWAY SYSTEM | RAIL |  | 4 | 5 | Critical | Defining maintenance standards Defining roles, responsibilities and competence for all parties in railway system | 3 | 5 | Significant | VR Track Oy GoU, Railway Operator and Infrastructure Manager | First draft of the maintenance standards has been done (VR Track Oy) | PARTIALLY IMPLEMENTED | OPEN | 2017-09-01
26 | Risk workshop 2 3.11.2016 | Management of contingency / deviation situations is not planned (broken infrastruckture, broken rolling stock, accidents etc.) | Recovery time is increased and safety is compromised Delay to train traffic |  |  |  | X | RAILWAY SYSTEM | OPERATION |  | 5 | 3 | Significant | Defining roles, responsibilities and competence for all parties in railway system Safety management system for Infrastructure Manager and Railway Operator | 5 | 2 | Moderate | GoU, Railway Operator and Infrastructure Manager |  | OPEN | OPEN | 2017-09-01
27 | Risk workshop 2 3.11.2016 | Broken or worn out rolling stock | Damage to infrastructure or rolling stock can't operate at the speed of 80 km/h Derailment and/or traffic delays for other rolling stock |  |  |  | X | RAILWAY SYSTEM | OPERATION |  | 4 | 4 | Significant | Defining roles, responsibilities and competence for all parties in railway system Safety management system for Infrastructure Manager and Railway Operator Inspection guideline for rolling stock | 3 | 4 | Moderate | GoU, Railway Operator and Infrastructure Manager |  | OPEN | OPEN | 2017-08-24
28 | Field trip in Uruguay, Toni Hytönen 1.12.2016 | Railway work without proper guidelines and rules | Locating errors, missing safeguard for railway traffic Derailment, collision |  |  |  | X | RAILWAY SYSTEM | OPERATION |  | 4 | 5 | Critical | Defining roles, responsibilities and competence for all parties in railway system Safety management system for Infrastructure Manager and Railway Operator | 1 | 5 | Moderate | GoU, Railway Operator and Infrastructure Manager |  | OPEN | OPEN | 2017-08-24
29 | Field trip in Uruguay, Toni Hytönen 1.12.2016 | Critical railway markings are missing | Unit speeding / locating errors Derailment |  |  |  | X | RAILWAY SYSTEM | SIGNALLING |  | 3 | 5 | Significant | Defining principles of railway marking Defining maintenance standards | 3 | 5 | Significant | Infrastructure Manager | First draft of the maintenance standards has been done (VR Track Oy) | PARTIALLY IMPLEMENTED | OPEN | 2017-09-01
30 | Design, Saara Vihma / Toni Hytönen 14.12.2016 | Tracks running in the trench below ground level | Pedestrian or animals on the tracks inside the trench. Accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | TRENCH AND TRACK | Speed at most 50 km/h | 5 | 4 | Critical | Width of the trench should allow avoidance of the rolling stock in an emergency | 3 | 4 | Moderate |  |  | OPEN | OPEN | 2017-08-24
31 | Design, Saara Vihma / Toni Hytönen 14.12.2016 | Tracks running in the trench below ground level | Pedestrian or animals falls into the trench. Personal casuality / accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | TRENCH AND TRACK | Speed at most 50 km/h | 3 | 4 | Moderate | Fall protection along the trench Design of the support beam / fenching the support beam reaching over the trech to prevent people from crossing trench | 2 | 4 | Moderate |  |  | OPEN | OPEN | 2017-08-24
32 | Design, Saara Vihma / Toni Hytönen 14.12.2016 | Tracks running in the trench below ground level | Flooding of the trench during heavy rain Work accident during construction, traffic delays in operation |  | X |  | X | RAILWAY SYSTEM | TRENCH |  | 5 | 3 | Significant | Draining with gravity Draining with pumps if gravity is not applicable. Ensuring constant power output for pumps and redundancy Draining with pumps or gravity during construction | 3 | 3 | Moderate |  |  | OPEN | OPEN | 2017-08-24
33 | Design, Saara Vihma / Toni Hytönen 14.12.2016 | Tracks running in the trench below ground level | Throwing rocks and other objects onto the tracks Damage to rolling stock |  |  |  | X | RAILWAY SYSTEM | TRENCH AND TRACK | Speed at most 50 km/h | 5 | 2 | Moderate | Fall protection along the trench | 4 | 2 | Minor |  |  | OPEN | OPEN | 2017-08-24
34 | Appendix C comments 7.1.2017 | Conflict with Departmental and Local authorities | Effects on project timetable and costs | X | X | X |  | TIMETABLE AND COST | PROJECT | MTOP and AFE have had conversations and cooperation with Montevideo and Canelones municipalities especially concerning Metropolitan area |  |  | TBD | Maintain cooperation with municipalities and other authorities during the whole project |  |  | TBD |  |  | OPEN | OPEN | 2017-06-27
35 | Appendix C comments 7.1.2017 | Project polarization on political terms | Effects on project timetable and costs | X | X | X |  | TIMETABLE AND COST | PROJECT |  |  |  | TBD | Maintain a coordinated work with the Government, work with a communication plan |  |  | TBD |  |  | OPEN | OPEN | 2017-06-27
36 | Appendix C comments 7.1.2017 | Over cost of the Project due financing issues | Effects on project costs | X | X | X |  | TIMETABLE AND COST | PROJECT |  |  |  | TBD | Design a good financing frame solution promoting provisional local funds |  |  | TBD |  |  | OPEN | OPEN | 2017-06-27
37 | Appendix C comments 7.1.2017 | Over cost due lacks of suppliers that comply with the high quality requirements of the projects | Effects on project timetable and costs |  | X | X |  | TIMETABLE AND COST | PROJECT |  |  |  | TBD | Investigate, promote and incentive local and regional supply companies |  |  | TBD |  |  | OPEN | OPEN | 2017-06-27
38 | Appendix C comments 7.1.2017 | Opposition of institutions and public persons to railway alignment or level crossing solutions | Effects on project timetable and costs | X |  |  |  | TIMETABLE AND COST | PROJECT |  |  |  | TBD | Establish a communication plan that include 3 level of Government and promote the benefits of project in the economy and local capacities |  |  | TBD |  |  | OPEN | OPEN | 2017-06-27
39 | Appendix C comments 7.1.2017 | Project technical requirements over the local and regional construction companies capacities | Quality deviation, effects on project timetable and costs |  | X | X | X | TIMETABLE AND COST | PROJECT |  |  |  | TBD | Development engineering solution according local and regional capacity |  |  | TBD |  | EN-standards have been adobted. | PARTIALLY IMPLEMENTED | OPEN | 2017-09-01
40 | Appendix C comments 7.1.2017 | Technical projects delayed due AFE no capacity to analyze and approved the several Bridges, Level Crossing and all the rest of technical projects included on the project | Quality deviation, effects on project timetable and costs | X | X | X |  | TIMETABLE AND COST | PROJECT |  |  |  | TBD | Establish a program to allow AFE improve the capacity (own capacity or Railway Contractor support capacity) to comply with Infrastructure role issues and review – study – adjust and approve the technical projects according the general schedule of new pulp plant project |  |  | TBD |  |  | OPEN | OPEN | 2017-06-27
41 | Appendix C comments 7.1.2017 | Delay or Block of Railway phase due incompatible procedure with national rules and laws for investing state funds | Effects on project timetable and costs | X | X | X |  | TIMETABLE AND COST | PROJECT |  |  |  | TBD | Establish a process for CREMA contact with a double approve process, guarantee the UPM and GOU approved process to implement and financing Railway Infrastructure project |  |  | TBD |  |  | OPEN | OPEN | 2017-06-27
42 | Road and street 6.6.2017 | Working arrengements for road traffic during construction of the trench under the highway (Uruguayn Yan) | Delays to road traffic |  | X |  |  | TIMETABLE AND COST | TRENCH |  | 5 | 1 | Minor |  |  |  | TBD |  |  |  | OPEN | 2017-08-24
43 | Geo 6.6.2017 | Embankment settlement is unbalanced (new embankment vs. current embankment settlement) | More need for maintenance Trafic delays because of speed limits |  |  |  | X | RAILWAY SYSTEM | GEOTECHNICS |  | 5 | 2 | Moderate | Embankment settlement test Using geogrid structure Defining maintenance standards | 5 | 1 | Minor | Railway Contractor | Some embankment settlement test have been done. Tests failed. First draft of the maintenance standards has been done. (VR Track Oy) | PARTIALLY IMPLEMENTED | CONTROLLED | 2017-09-01
44 | Geo 6.6.2017 | Not enough information from ground surveys | Insufficient ground surveys during design phase Designing with assumptions that could lead to false conclusions Effects on project timetable and costs | X | X |  |  | TIMETABLE AND COST | GEOTECHNICS |  | 4 | 4 | Significant | Additional ground surveys in construction design | 2 | 4 | Moderate | Railway Contractor | Some surveys have been done and more surveys and survey plans will be / is been done | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
45 | Geo 6.6.2017 | Ground and perch water level unknown | Construction below ground water level can cause unstable structures Effects on project timetable and costs | X | X |  |  | TIMETABLE AND COST | GEOTECHNICS |  | 4 | 2 | Minor | Additional ground and perch water level surveys | 3 | 2 | Minor | Railway Contractor |  | OPEN | CONTROLLED | 2017-08-24
47 | Rail and operation 7.6.2017 | Long and steep hills, over 2 km arise | Rolling stock can't accelerate on the hill side and worst case rolling stock gets stuck on the hill side. Traffic delays |  |  |  | X | RAILWAY SYSTEM | RAIL |  | 5 | 2 | Moderate | Safety management system for Infrastructure Manager and Railway Operator | 5 | 1 | Minor | GoU, Railway Operator and Infrastructure Manager | Geometry and traffic planning has considered the risk as much as possible. | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
48 | Bridge 14.6.2017 | Insufficient ground surveys around bridge structures | Design is based on assumptions. Problems e.x.: collapse of casting mold. Effects on project timetable and costs | X | X |  |  | TIMETABLE AND COST | BRIDGE | Ground surveys of the pre-engineerin phase II | 5 | 2 | Moderate | Additional ground surveys in construction design | 5 | 1 | Minor | Railway Contractor |  | OPEN | OPEN | 2017-08-24
49 | Bridge 14.6.2017 | Constructing demanding / special skill structures in a narrow urban environment: - piling - transportation and lifting of elements | Damaging surrounding structures Trafic delays |  | X |  |  | TIMETABLE AND COST | BRIDGE |  | 5 | 2 | Moderate | Work area plan and safety plan | 5 | 2 | Moderate | Railway Contractor |  | OPEN | OPEN | 2017-09-01
50 | Bridge 14.6.2017 | The number of bridge and skill structures in the project is significant | Demanding structures, it is likely that some problems occur Effects on project timetable and costs |  | X |  |  | TIMETABLE AND COST | BRIDGE | Element bridges are preferred and the number of bridge types are limited Level crossings are kept | 3 | 4 | Moderate | Ensuring enough resources for bridge and skill structures | 2 | 4 | Moderate | Railway Contractor |  | OPEN | OPEN | 2017-09-01
51 | Bridge 14.6.2017 | Tensioned bridge structure | Know-how for tensioned bridge structures is limited or unavailable Effects on project timetable and costs |  | X |  |  | TIMETABLE AND COST | BRIDGE |  | 4 | 3 | Moderate | Ensuring enough expertize for tensioned bridge structures | 3 | 3 | Moderate | Railway Contractor |  | OPEN | OPEN | 2017-09-01
52 | Bridge 14.6.2017 | Old track embankment can't be used to transport elements | Old track embankment is not stable enough or not available Effects on project timetable and costs |  | X |  |  | TIMETABLE AND COST | BRIDGE |  | 5 | 1 | Minor | [7 empty] | CONTROLLED | 2017-08-24
53 | Bridge 14.6.2017 | A bridge that is difficult to reach | Elements or ready-mixed concrete can't be transported to construction site Effects on project timetable and costs |  | X |  |  | TIMETABLE AND COST | BRIDGE |  | 4 | 2 | Minor | [7 empty] | CONTROLLED | 2017-08-24
54 | Rail and operation 7.6.2017 | Tracks running in the trench below ground level | Rolling stock in fire inside trench or tunnel section Combustion gases causes health issues |  |  |  | X | RAILWAY SYSTEM | RAIL |  | 3 | 4 | Moderate | Defining roles, responsibilities and competence for all parties in railway system Safety management system for Infrastructure Manager and Railway Operator | 2 | 3 | Minor | GoU, Railway Operator and Infrastructure Manager |  | OPEN | OPEN | 2017-08-24
55 | Rail and operation 7.6.2017 | Passenger stations inside the tunnel section | Diesel powered locomotives causes exhaust gases Health issues |  |  |  | X | RAILWAY SYSTEM | TRENCH AND TRACK | No tunnel section for passanger station |  |  | TBD |  |  |  | TBD |  |  |  | REMOVED | 2017-08-24
57 | Trench 15.6.2017 | Cables, pipes, severs and other structures below ground level | Cables, pipes, severs and other structures are unknown, damage in construction Effects on project timetable and costs |  | X |  |  | ENVIRONMENT AND SOCIAL | TRENCH |  | 5 | 3 | Significant | Surveys of cables and other structures and cable scanning before digging | 4 | 3 | Moderate | Railway Contractor |  | OPEN | OPEN | 2017-08-24
58 | Trench 15.6.2017 | Anchoring and constructing the support wall | Damage to structures / anchoring outside the railway area Effects on project timetable and costs |  | X |  |  | ENVIRONMENT AND SOCIAL | TRENCH |  | 5 | 4 | Critical | Environment Impact Assessment and permitting Surveys of cables and other structures and cable scanning before digging Work and safety plan | 3 | 4 | Moderate | LKSur Railway Contractor |  | OPEN | OPEN | 2017-08-24
60 | Signalling 10.8.2017 | Operation rulebook is not ready for the commissioning and for the training | Training for the new signalling system takes time and requires the final operation rulebook Impact on projects timetable |  |  | X | X | RAILWAY SYSTEM | SIGNALLING |  | 5 | 3 | Significant | Training plan and plan for the commissioning | 2 | 3 | Minor | GoU Railway Operator Infrastructure Manager Railway Contractor |  | OPEN | OPEN | 2017-08-24
61 | Signalling 10.8.2017 | Some of the trains have ATP and some don't have ATP | Unit speed and signalling messages are not controlled by ATP Collision |  |  |  | X | RAILWAY SYSTEM | SIGNALLING |  | 3 | 5 | Significant | Operation rulebook Training plan and plan for the commissioning | 1 | 5 | Moderate | GoU Railway Operator Infrastructure Manager Railway Contractor |  | OPEN | OPEN | 2017-08-24
62 | Signalling 10.8.2017 | Resources and competence for commissioning in multiple locations at the same time | Not enough resources for commissioning or not enough competence to chech the system before use Impact on timetable and/or safety issues |  |  | X |  | RAILWAY SYSTEM | SIGNALLING |  | 4 | 3 | Moderate | Training plan and plan for the commissioning | 2 | 3 | Minor | GoU Railway Operator Infrastructure Manager Railway Contractor |  | OPEN | OPEN | 2017-08-24
63 | Signalling 10.8.2017 | Signalling system changes after commissioning | System changes are not managed for safety and functionally Safety and functional issues |  |  |  | X | RAILWAY SYSTEM | SIGNALLING |  | 2 | 5 | Significant | Prosedures for the modification of the Signalling System | 1 | 5 | Moderate | Infrastructure Manager |  | OPEN | OPEN | 2017-08-24
64 | Bridge 15.8.2017 | Current steel bridge materials | Material properties and corrosion levels are not known. Bridge collapses during use |  | X |  | X | RAILWAY SYSTEM | BRIDGE |  | 1 | 5 | Moderate | Samples of the bridge materials | 1 | 5 | Moderate | Railway Contractor |  | OPEN | OPEN | 2017-08-24
64 | Construction and Maintenance 16.7.2017 | Quality requirements for design and construction are missing | National quideline for quality requirements (procedures, limits etc.) are missing Quality assurance or commissioning are not possible | X | X |  |  | TIMETABLE AND COST | PROJECT |  | 3 | 5 | Significant | Defining quality requirements for detail design and construction phase | 2 | 3 | Minor | GoU | Construction quality standards defined partly in pre-engineering (VR Track Oy). | OPEN | OPEN | 2017-09-01
65 | Bridge 15.8.2017 | Current steel bridge rivet | Condition of the rivet connections are not known. Bridge collapses during use |  | X |  | X | RAILWAY SYSTEM | BRIDGE |  | 2 | 5 | Significant | Inspection of all rivet connections | 1 | 5 | Moderate | Railway Contractor |  | OPEN | OPEN | 2017-08-24
65 | Construction and Maintenance 16.7.2017 | Availability, storage and quality of materials (eg rail, sleepers, points, signalling) | The materials required by the project are not available to the required extent or they do not meet the requirements Effects on project timetable and costs |  | X |  |  | TIMETABLE AND COST | PROJECT |  | 3 | 5 | Significant | Starting of material sourcing as soon as possible | 1 | 5 | Moderate | GoU |  | OPEN | OPEN | 2017-08-24
66 | Bridge 15.8.2017 | Current steel bridges are founded on stone abuntments | Condition of stone abuntments are not know Damage to bridge structures |  | X |  | X | RAILWAY SYSTEM | BRIDGE |  | 2 | 3 | Minor |  | 2 | 3 | Minor |  |  |  | CONTROLLED | 2017-08-24
66 | Construction and Maintenance 16.7.2017 | Weather conditions (heavy rain, storms) | Damage to construction site road or support structure Effects on project timetable and costs |  | X |  |  | TIMETABLE AND COST | PROJECT |  | 4 | 3 | Moderate | Safety and operation plan Mapping of the risk areas | 2 | 3 | Minor | Railway Contractor |  | OPEN | OPEN | 2017-08-24
67 | Bridge 15.8.2017 | Other old abuntmens | Condition of abuntments are not know Bridge collapses during use |  | X |  | X | RAILWAY SYSTEM | BRIDGE |  | 3 | 5 | Significant | New abuntmens for small bridges | 1 | 2 | Negligible | Railway Contractor |  | OPEN | OPEN | 2017-08-24
67 | Construction and Maintenance 16.7.2017 | Availability of manpower | Availability of local manpower and strong unions (strikes) Effects on project timetable and costs |  | X |  |  | TIMETABLE AND COST | PROJECT |  | 5 | 3 | Significant | Agreement of the Railway Contractor and GoU Dialogue with unions | 4 | 3 | Moderate | GoU |  | OPEN | OPEN | 2017-09-01
68 | Construction and Maintenance 16.7.2017 | Competence of manpower | Competence of local manpower is not on the required level Effects on project timetable and costs, quality issues |  | X |  |  | TIMETABLE AND COST | PROJECT |  | 3 | 2 | Minor | Competence requirements for the used manpower of the critical components and structures (e.x. bridge, points, signalling) | 2 | 2 | Negligible | GoU |  | OPEN | CONTROLLED | 2017-09-01
69 | Road and street 23.8.2017 | Number of level crossings especially in centre of Montevideo | Vaikutukset liikennöintiin häiriötilantEIAsa Accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | ROAD AND STREET | Almost 240 level crossings | 4 | 4 | Significant | List of railway level crossings' properties and measures. Measures for fault situations Maintenance plan | 4 | 4 | Significant | GoU | List of railway level crossings' properties and measures and type designs has been done. (VR Track Oy) | PARTIALLY IMPLEMENTED | OPEN | 2017-08-24
70 | Road and street 23.8.2017 | Some special needs for level crossings maybe unknown | Animal routes, factory or other private needs Insufficient safety equipment for the level crossing | X |  |  | X | RAILWAY SYSTEM | ROAD AND STREET | Study of the current situation | 1 | 4 | Minor | Public meetings and additional surveys if needed | 1 | 4 | Minor | GoU |  | OPEN | CONTROLLED | 2017-08-24
71 | Road and street 23.8.2017 | Double barries on some level crossings | Vehicle gets stuck in between barries Accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | ROAD AND STREET |  | 3 | 4 | Moderate | Type drawings of the level crossings includes middle platform between lanes. | 2 | 4 | Moderate | VR Track Oy | List of railway level crossings' properties and measures and type designs has been done. (VR Track Oy) | IMPLEMENTED | OPEN | 2017-08-24
72 | Road and street 23.8.2017 | Vandalism | Damage to the level crossing markings or safety equipment Accidents to persons caused by rolling stock in motion |  |  |  | X | RAILWAY SYSTEM | ROAD AND STREET |  | 3 | 4 | Moderate | Measures for fault situations Maintenance plan | 2 | 4 | Moderate | GoU |  | OPEN | OPEN | 2017-08-24
73 | Geo 24.8.2017 | Subground and material bearing capacity unknown | Structual layers are too thin, bearing capacity is insufficient Trafic delays because of speed limits and more need for maintenance. Ultimately derailment. |  |  |  | X | RAILWAY SYSTEM | GEOTECHNICS |  | 5 | 3 | Significant | Increasing thickness of the structual layers Stabilization of the subground Bearing capacity test Quality assurance for the material | 3 | 3 | Moderate | Railway Contractor |  | OPEN | OPEN | 2017-08-24
74 | Geo 24.8.2017 | Ground and perch water level unknown | Construction below ground water level can cause unstable structures Effects on project timetable and costs |  | X |  |  | RAILWAY SYSTEM | TRENCH |  | 5 | 2 | Moderate | Water proof structure Additional ground and perch water level surveys | 4 | 2 | Minor | Railway Contractor |  | OPEN | OPEN | 2017-08-24

## RISK MATRIX
RISK MATRIX FOR RISK EVALUATION
Railway Project, Pre-engineering phase 2
2017-07-19
SEVERITY OF CONSEQUENCES
| Consequense | 1 Negligible | 2 Minor | 3 Moderate | 4 Significant | 5 Severe
| Personal casualty | Negligible injury | Minor injury, sick leave under 5 days | Moderate injury, sick leave over 14 days | Death or significant injury, sick leave over 30 days | Multiple deaths or significant injuries
| Property damage | Negligible property damage > 10 000 $ | Minor property damage > 50 000 $ | Moderate property damage > 100 000 $ | Significant property damage > 200 000 $ | Severe property damage > 1 000 000 $
| Project impact | Negligible impact on timetable or costs > 1 day or > 50 000 $ | Minor impact on timetable or costs < 1 weeks delay or < 100 000 $ | Moderate impact on timetable or costs > 1 week delay in project or > 200 000 $ cost | Significant impact on timetable or costs > 2 weeks delay in project or > 500 000 $ cost | Severe impact on timetable or costs > 1 month delay in project or > 5 000 000 $ cost
| Railway or road accident | Near miss or neglidible accident - no delay | Minor accident Rail traffic delay less than 4 hours or major road closed for 1 hour | Moderate traffic accident Rail traffic delay less than 8 hours or major road closed for 4 hours | Significant traffic accident Rail traffic delay less than 12 hours or major road closed for 8 hours | Severe traffic accident Rail traffic delay over 16 hours or major road closed for 12 hours
| Environmental impact | Negligible environmental impact, no need for actions | Minor environmental impact, easily repairable | Moderate environmental impact, repairable | Significant environmental impact in large area, not easily repairable | Severe environmental impact, not fully repairable
PROBABILITY | 5 Very likely Occurs at least 10 times per year. | Minor | Moderate | Significant | Critical | Critical | Insignificant | Acceptable risk
| 4 Likely Occurs at least once per year. | Insignificant | Minor | Moderate | Significant | Critical | Minor | Acceptable risk, follow up if necessary
| 3 Possible Occurs at least once per 10 years. | Insignificant | Minor | Moderate | Moderate | Significant | Moderate | Measures must be planned
| 2 Unlikely Occurs at least once per 50 years | Insignificant | Insignificant | Minor | Minor | Moderate | Significant | Measures must be planned and implemented
| 1 Very Unlikely Occurs less than once per 50 years. | Insignificant | Insignificant | Insignificant | Insignificant | Minor | Critical | Immediate measures must be planned and implemented

## WORKSHOPS
WORKSHOPS AND PARTICIPANTS IN RISK ASSESSMENT
Railway Project, Pre-engineering phase 2
NAME | COMPANY | TITLE | RISK WORKSHOP 1 21.10.2016 | RISK WORKSHOP 2 3.11.2016 | RISK WORKSHOP 3 7.11.2016 | RISK WORKSHOP 4 9.11.2016 | MEETING 28.11.2016 | ROAD, STREET AND GEO 6.6.2017 | RAIL TRACK AND OPERATION 7.6.2017 | BRIDGE 14.6.2017 | TRENCH 15.6.2017 | ENVIRONMENT with LKSur 29.6.2017 | ROAD, WATER, ENVIRONMENT CSI expert interview 30.6.2017 | SIGNALLING 10.8.2017 | CONSTRUCTION AND MAINTENANCE 16.8.2017 | PROJECT RISKS 22.8.2017 | ROAD AND STREET 23.8.2017 | GEO AND RAIL 24.9.2017
Agustin Casares | CSI | Transport planning, traffic studies and traffic models | [10 empty] | X
Gisele Píngaro | CSI | Roads and Transportation | [10 empty] | X
Santiago Symonds | CSI | Hydraulics and Environment | [10 empty] | X
Santiago Urrestarazu | CSI | Hydraulics and Environment | [10 empty] | X
Jorma Paananen | Fimpec | Construction and Maintenance | [12 empty] | X
Gabriel dos Santos | LKSur | Environment | [9 empty] | X
Nicolas Rehermann | LKSur | Environment | [9 empty] | X
Gervasio Gonzalez | UPM | Environment | [9 empty] | X
Magdalena Ibanez | UPM | Social and environment |  |  |  |  | X
Päivi Salpakivi | UPM | Social and environment |  |  |  |  | X
Auli Vanhoja | VR Track Oy | Geotechnics | [5 empty] | X |  |  | X | [6 empty] | X
Harju Outi | VR Track Oy | Level crossings | [14 empty] | X
Harri Etelämäki | VR Track Oy | Level crossings | [5 empty] | X
Ilkka Tiiro | VR Track Oy | Bridge | [7 empty] | X
Janne Wuorenjuuri | VR Track Oy | Specialist |  | X |  | X | [9 empty] | X
Jooel Juntunen | VR Track Oy | Construction and Maintenance | [12 empty] | X
Jouni Mikkonen | VR Track Oy | Environmental specialist | X |  | X
Jussi Sipilä | VR Track Oy | Traffic specialist |  | X |  | X |  |  | X | [6 empty] | X
Kai Kiihtelys | VR Track Oy | Signalling | [11 empty] | X
Maiju Storhammar | VR Track Oy | Level crossings | [5 empty] | X | [8 empty] | X
Outi Erälaukko | VR Track Oy | Safety specialist |  | X | X |  |  | X | X
Saara Vihma | VR Track Oy | Traffic specialist | X | X | X | X |  |  | X | [6 empty] | X |  | X
Tero Savolainen | VR Track Oy | Construction and Maintenance | [12 empty] | X
Tiina Kiuru | VR Track Oy | Project manager | [15 empty] | X
Tomi Lindgren | VR Track Oy | Road and street |  |  |  |  | X | X | [8 empty] | X
Toni Hytönen | VR Track Oy | Head of risk management group | X | X | X | X | X | X | X |  | X | X | X | X | X |  | X | X

## OVERVIEW
RISK LEVEL | PCS
Insignificant | 0
Minor | 11
Moderate | 21
Significant | 20
Critical | 9
TBD | 9
LIFECYCLE PHASE | PCS
DESIGN | 14
CONSTRUCTION | 39
COMMISSIONING | 10
OPERATION | 40
HAZARD TYPE | PCS
TIMETABLE AND COST | 23
RAILWAY SYSTEM | 35
WORK SAFETY | 0
ENVIRONMENT AND SOCIAL | 12
STATE OF HAZARD | PCS
OPEN | 56
CONTROLLED | 13
REMOVED | 1
STATE OF MEASURES | PCS
OPEN | 41
PARTIALLY IMPLEMENTED | 21
IMPLEMENTED | 3
RESIDUAL RISK LEVEL | PCS
Insignificant | 0
Minor | 18
Moderate | 28
Significant | 8
Critical | 0
TBD | 10
Number of identifyed hazards | 70
COLOR CODES
| R | G | B
Insignificant | 51 | 153 | 102
Minor | 204 | 255 | 204
Moderate | 255 | 255 | 0
Major | 255 | 102 | 0
Critical | 255 | 0 | 0

## REMOVED RISKS (hidden)
REMOVED HAZARDS
Railway Project, Pre-engineering phase 2
SECRET
[12 empty] | RISK ESTIMATION |  |  |  | RESIDUAL RISK ESTIMATION
REASON | HAZARD ID | HAZARD IDENTIFIED AT | HAZARD | HAZARDOUS SITUATION AND CONSEQUENCES | DESIGN | CONSTRUCTION | PLACING IN SERV. | OPERATION | HAZARD TYPE | DISCIPLINE | EXISTING MEASURES AND ASSUMPTIONS | FREQUENCY | SEVERITY | RISK LEVEL | MEASURES | FREQ. RES. | SEV. RES. | RESIDUAL RISK LEVEL | PERSON/ORGANIZATION IN CHARGE | IMPLEMENTED SAFETY MEASURES /REQUIREMENTS | STATE OF SAFETY MEASURES | STATE OF HAZARD | UPDATE
DUPLICATE WITH 022 | 23 | Risk workshop 2 3.11.2016 | Angle between track and road is too tight | Pedestrian or vehicle can't detect incoming train Accidents to persons caused by rolling stock in motion |  |  |  | X | Railway system | ROAD AND STREET | Speed limit 60 km/h for train traffic in city area. | 4 | 4 | Significant | A) List of railway level crossings' properties and measures. | 4 | 4 | Significant | TBD | A) Level crossing action plan | OPEN | OPEN | 2017-06-06
DUPLICATE WITH 013 | 14 | Risk workshop 2 3.11.2016 | Stations and platforms in rural areas are used for accommodation, parking and other activities | Unauthorized personel on the rail tracks. Accidents to persons caused by rolling stock in motion |  |  |  | X | Railway system | RAIL |  | 4 | 4 | Significant | A) Study of the current situation. B) Measures for each target C) Public meetings, education and information | 4 | 4 | Significant | TBD | A) not yet implemented B) not yet implemented C) not yet implemented | OPEN | OPEN | 2017-06-07
DUPLICATE WITH 013 | 15 | Risk workshop 2 3.11.2016 | All day and more frequent traffic with higher speed | Unauthorized personel on the rail tracks. Accidents to persons caused by rolling stock in motion |  |  |  | X | Railway system | RAIL |  | 4 | 4 | Significant | A) Safety measures needed for rolling stock (ex. headlights and horn) B) Public meetings, education and information | 4 | 4 | Significant | TBD | A) not yet implemented B) not yet implemented | OPEN | OPEN | 2017-06-07
DUPLICATE WITH 013 | 17 | Risk workshop 2 3.11.2018 | Railway area is not physically or visually separated from surrounding area | Unauthorized personel on the rail tracks. Accidents to persons caused by rolling stock in motion |  |  |  | X | Railway system | RAIL |  | 4 | 4 | Significant | A) Defining and separating area needed for railway physically and visually B) Fenching certain railway areas, restricted area signs | 4 | 4 | Significant | TBD | A) not yet implemented B) not yet implemented | OPEN | OPEN | 2017-06-07
DUPLICATE WITH 019 | 20 | Risk workshop 2 3.11.2021 | Vandalism | Breaking, demolishing or stealing track equiment / rolling stock / Collision, derailment |  |  |  | X | Railway system | RAIL |  | 2 | 5 | Significant | A) Covering signaling cables B) Camera surveillance on stations and platforms | 2 | 5 | Significant | TBD | A) not yet implemented B) not yet implemented | OPEN | OPEN | 2017-06-07
DUPLICATE WITH 009 | 56 | Trench 15.6.2017 | Transporting large amount of mass in urban environment | Traffic accident, noice from the trucks, congestation. |  | X |  |  | Environment and social | GEO |  | 3 | 4 | Moderate | A) Transportation plan for construction traffic B) Construction site plan | 3 | 4 | Moderate |  |  |  | OPEN | 2017-06-27
DUPLICATE WITH 032 | 59 | Trench 15.6.2017 | Draining of the trench | Draining is not effective to drain the trench especially with pumps if gravity draining is not possible. / Pumps not working during power out Traffic delays |  |  |  | X | Environment and social | TRENCH |  | 4 | 4 | Significant | A) Ensuring constant power output for pumps B) Redundancy | 4 | 4 | Significant |  |  |  | OPEN | 2017-06-27
DUPLICATE WITH 027 | 46 | Rail and operation 7.6.2017 | Broken or worn out rolling stock | Rolling stock can't operate at the speed of 80 km/h Traffic delays for other rolling stock |  |  |  | X | RAILWAY SYSTEM | OPERATION | Current model for inspection and placing in use for rolling stock? | 5 | 2 | Moderate | M31) Inspection and placing in use processes for rolling stock | 5 | 1 | Minor |  |  | OPEN | OPEN | 2017-06-27